## Gantt
Interference Injection Tool
Team: 1
| Project start date | 2025-11-05
| Project end date | 2026-06-12 |  |  |  | Nov | [25 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr | [29 empty] | May | [30 empty] | Jun
[6 empty] | 45 |  |  |  |  | 46 | [6 empty] | 47 | [6 empty] | 48 | [6 empty] | 49 | [6 empty] | 50 | [6 empty] | 51 | [6 empty] | 52 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27
 | time axis 2025-11-05 to 2026-06-30
 | time axis 2025-11-05 to 2026-06-30
| Task | Assigned to | Progress | Start | End | time axis 2025-11-05 to 2026-06-30
| Requirement analysis |  |  | 2025-11-05 | 2025-11-19
| Clarify requirements | Business analyst | 100 | 2025-11-05 | 2025-11-19
| Design |  |  | 2025-11-12 | 2025-11-24
| Decide on technologies and frameworks | Solution Architect | 50 | 2025-11-12 | 2025-11-13
| Create UI/UX design | UI/UX designer | 0 | 2025-11-12 | 2025-11-19
M | Create technical specification | Solution Architect | 0 | 2025-11-17 | 2025-11-24
| Development |  |  | 0 | 0
Develop Add interference tab
| Develop import clean signal | Developer | 0
| Visualize clean signal | Developer | 0
| Develop import interference | Developer | 0
| Visualize interference | Developer | 0
| Develop interference parameter adjustments | Developer | 0
| Visualize adjustments | Developer | 0
| Develop interference injection | Developer | 0
| Develop signal processing | Developer | 0
| Develop export functionality | Developer | 0
Develop analyze export tab
| Visulize interfered signal | Developer | 0
| Develop statistical analysis | Developer | 0
| Develop export analysis | Developer | 0
| Testing |  |  | 0 | 0
| Prepare test cases | Tester | 0
| Perform tests | Tester | 0
| Correct bugs | Developer | 0
| Deployment |  |  | 0 | 0
| Deploy application | Solution architect / Developer | 0
| Update technical specification | Solution Architect | 0
| Write user manual | Business analyst | 0
| Project presentation |  |  | 2026-06-01 | 2026-06-12
| Prepare final presentation | Team | 0 | 2026-06-01 | 2026-06-11
| Present the project | Team | 0 | 2026-06-12 | 2026-06-12